## Sheet1
title | Atlas Sprint Schedule | type | name | start | end | display | timepuml | completePuml | type2 | @startgantt | Sprint 00 | Architect | @startgantt | Ideate
Starting Sprint | 0 | increment | Ideate | 2024-11-19 | 2024-12-19 | Ideate | [Ideate] starts on 2024-11-19 and ends on 2024-12-19 | [Ideate] is 100% complete | increment | <style> | Sprint 01 | Design |  | Proof of Concept
header |  | increment | Proof of Concept | 2024-12-20 | 2025-03-19 | Proof of Concept | [Proof of Concept] starts on 2024-12-20 and ends on 2025-03-19 | [Proof of Concept] is 100% complete | increment | ganttDiagram { | Sprint 02 | Backend | <style> | Prototype
footer | generated: %date("YYYY-MM-dd") |  | Architect | 2024-12-20 | 2025-01-03 | Sprint 00: Architect | [Sprint 00: Architect] starts on 2024-12-20 and ends on 2025-01-03 | [Sprint 00: Architect] is 100% complete | sprint | task { | Sprint 03 | Frontend | ganttDiagram { | Restricted Preview
caption |  |  | Design | 2025-01-04 | 2025-01-18 | Sprint 01: Design | [Sprint 01: Design] starts on 2025-01-04 and ends on 2025-01-18 | [Sprint 01: Design] is 100% complete | sprint | BackGroundColor #ffe6e6 | Sprint 04 | Integrate | task { | Invite Preview
scale | projectscale monthly zoom 3 |  | Backend | 2025-01-19 | 2025-02-02 | Sprint 02: Backend | [Sprint 02: Backend] starts on 2025-01-19 and ends on 2025-02-02 | [Sprint 02: Backend] is 100% complete | sprint | LineColor White | Sprint 05 | Onboarding | BackGroundColor #ffe6e6
|  |  | Frontend | 2025-02-03 | 2025-02-17 | Sprint 03: Frontend | [Sprint 03: Frontend] starts on 2025-02-03 and ends on 2025-02-17 | [Sprint 03: Frontend] is 100% complete | sprint | } | Sprint 06 | Admin & Invites | LineColor White
Start | 2024-11-19 |  | Integrate | 2025-02-18 | 2025-03-04 | Sprint 04: Integrate | [Sprint 04: Integrate] starts on 2025-02-18 and ends on 2025-03-04 | [Sprint 04: Integrate] is 100% complete | sprint | undone { | Sprint 07 | Renderer R&D | }
End | 2026-02-18 |  | Onboarding | 2025-03-05 | 2025-03-19 | Sprint 05: Onboarding | [Sprint 05: Onboarding] starts on 2025-03-05 and ends on 2025-03-19 | [Sprint 05: Onboarding] is 100% complete | sprint | BackGroundColor LightGray | Sprint 08 | Quill Enhancements - pictures, tables | undone {
|  | increment | Prototype | 2025-03-20 | 2025-08-07 | Prototype | [Prototype] starts on 2025-03-20 and ends on 2025-08-07 | [Prototype] is 18% complete | increment | } | Sprint 09 | Markdown | BackGroundColor LightGray
back | #ffe6e6 |  | Admin & Invites | 2025-03-20 | 2025-04-09 | Sprint 06: Admin & Invites | [Sprint 06: Admin & Invites] starts on 2025-03-20 and ends on 2025-04-09 | [Sprint 06: Admin & Invites] is 100% complete | sprint | } | Sprint 10 | PlantUML & Latex | }
undone | LightGray |  | Renderer R&D | 2025-04-10 | 2025-04-24 | Sprint 07: Renderer R&D | [Sprint 07: Renderer R&D] starts on 2025-04-10 and ends on 2025-04-24 | [Sprint 07: Renderer R&D] is 29% complete | sprint | </style> | Sprint 11 | Content Safety API | }
|  |  | Quill Enhancements - pictures, tables | 2025-04-25 | 2025-05-09 | Sprint 08: Quill Enhancements - pictures, tables | [Sprint 08: Quill Enhancements - pictures, tables] starts on 2025-04-25 and ends on 2025-05-09 | [Sprint 08: Quill Enhancements - pictures, tables] is 0% complete | sprint | title Atlas Sprint Schedule | Sprint 12 | Structure Sharing | </style>
|  |  | Markdown | 2025-05-10 | 2025-05-24 | Sprint 09: Markdown | [Sprint 09: Markdown] starts on 2025-05-10 and ends on 2025-05-24 | [Sprint 09: Markdown] is 0% complete | sprint | projectscale monthly zoom 3 | Sprint 13 | Cross-Structure Reporting
|  |  | PlantUML & Latex | 2025-05-25 | 2025-06-08 | Sprint 10: PlantUML & Latex | [Sprint 10: PlantUML & Latex] starts on 2025-05-25 and ends on 2025-06-08 | [Sprint 10: PlantUML & Latex] is 0% complete | sprint | hide footbox | Sprint 14 | User Metrics | title Atlas Sprint Schedule
|  |  | Content Safety API | 2025-06-09 | 2025-06-23 | Sprint 11: Content Safety API | [Sprint 11: Content Safety API] starts on 2025-06-09 and ends on 2025-06-23 | [Sprint 11: Content Safety API] is 0% complete | sprint | footer generated: %date("YYYY-MM-dd") | Sprint 15 | Platform Metrics & Alerting | projectscale monthly zoom 3
|  |  | Structure Sharing | 2025-06-24 | 2025-07-08 | Sprint 12: Structure Sharing | [Sprint 12: Structure Sharing] starts on 2025-06-24 and ends on 2025-07-08 | [Sprint 12: Structure Sharing] is 0% complete | sprint | Project starts 2024-11-19 | Sprint 16 | Test Automation | hide footbox
|  |  | Cross-Structure Reporting | 2025-07-09 | 2025-07-23 | Sprint 13: Cross-Structure Reporting | [Sprint 13: Cross-Structure Reporting] starts on 2025-07-09 and ends on 2025-07-23 | [Sprint 13: Cross-Structure Reporting] is 0% complete | sprint | [Ideate] starts on 2024-11-19 and ends on 2024-12-19 | Sprint 17 | Web Analytics
|  |  | User Metrics | 2025-07-24 | 2025-08-07 | Sprint 14: User Metrics | [Sprint 14: User Metrics] starts on 2025-07-24 and ends on 2025-08-07 | [Sprint 14: User Metrics] is 0% complete | sprint | [Proof of Concept] starts on 2024-12-20 and ends on 2025-03-19 | Sprint 18 | LLM Ingest
|  | increment | Restricted Preview | 2025-08-08 | 2025-12-05 | Restricted Preview | [Restricted Preview] starts on 2025-08-08 and ends on 2025-12-05 | [Restricted Preview] is 0% complete | increment | [Sprint 00: Architect] starts on 2024-12-20 and ends on 2025-01-03 | Sprint 19 | Penetration Testing | footer generated: %date("YYYY-MM-dd")
|  |  | Platform Metrics & Alerting | 2025-08-08 | 2025-08-22 | Sprint 15: Platform Metrics & Alerting | [Sprint 15: Platform Metrics & Alerting] starts on 2025-08-08 and ends on 2025-08-22 | [Sprint 15: Platform Metrics & Alerting] is 0% complete | sprint | [Sprint 01: Design] starts on 2025-01-04 and ends on 2025-01-18 | Sprint 20 | Cost Optimization
|  |  | Test Automation | 2025-08-23 | 2025-09-06 | Sprint 16: Test Automation | [Sprint 16: Test Automation ] starts on 2025-08-23 and ends on 2025-09-06 | [Sprint 16: Test Automation ] is 0% complete | sprint | [Sprint 02: Backend] starts on 2025-01-19 and ends on 2025-02-02 | Sprint 21 | Automated Scaling
|  |  | Web Analytics | 2025-09-07 | 2025-09-21 | Sprint 17: Web Analytics | [Sprint 17: Web Analytics] starts on 2025-09-07 and ends on 2025-09-21 | [Sprint 17: Web Analytics] is 0% complete | sprint | [Sprint 03: Frontend] starts on 2025-02-03 and ends on 2025-02-17 | Sprint 22 | Payment Processing | Project starts 2024-11-19
|  |  | LLM Ingest | 2025-09-22 | 2025-10-06 | Sprint 18: LLM Ingest | [Sprint 18: LLM Ingest] starts on 2025-09-22 and ends on 2025-10-06 | [Sprint 18: LLM Ingest] is 0% complete | sprint | [Sprint 04: Integrate] starts on 2025-02-18 and ends on 2025-03-04 | Sprint 23 | Design Review
|  |  | Penetration Testing | 2025-10-07 | 2025-10-21 | Sprint 19: Penetration Testing | [Sprint 19: Penetration Testing] starts on 2025-10-07 and ends on 2025-10-21 | [Sprint 19: Penetration Testing] is 0% complete | sprint | [Sprint 05: Onboarding] starts on 2025-03-05 and ends on 2025-03-19 | Sprint 24 | Design Adaptation
|  |  | Cost Optimization | 2025-10-22 | 2025-11-05 | Sprint 20: Cost Optimization | [Sprint 20: Cost Optimization] starts on 2025-10-22 and ends on 2025-11-05 | [Sprint 20: Cost Optimization] is 0% complete | sprint | [Prototype] starts on 2025-03-20 and ends on 2025-08-07 | Sprint 25 | Regulatory Review
|  |  | Automated Scaling | 2025-11-06 | 2025-11-20 | Sprint 21: Automated Scaling | [Sprint 21: Automated Scaling] starts on 2025-11-06 and ends on 2025-11-20 | [Sprint 21: Automated Scaling] is 0% complete | sprint | [Sprint 06: Admin & Invites] starts on 2025-03-20 and ends on 2025-04-09 | Sprint 26 | User Acq. & Marketing plan
|  |  | Payment Processing | 2025-11-21 | 2025-12-05 | Sprint 22: Payment Processing | [Sprint 22: Payment Processing] starts on 2025-11-21 and ends on 2025-12-05 | [Sprint 22: Payment Processing] is 0% complete | sprint | [Sprint 07: Renderer R&D] starts on 2025-04-10 and ends on 2025-04-24 | Sprint 27 | Business Plan
|  | increment | Invite Preview | 2025-12-06 | 2026-02-18 | Invite Preview | [Invite Preview] starts on 2025-12-06 and ends on 2026-02-18 | [Invite Preview] is 0% complete | increment | [Sprint 08: Quill Enhancements - pictures, tables] starts on 2025-04-25 and ends on 2025-05-09
|  |  | Design Review | 2025-12-06 | 2025-12-20 | Sprint 23: Design Review | [Sprint 23: Design Review] starts on 2025-12-06 and ends on 2025-12-20 | [Sprint 23: Design Review] is 0% complete | sprint | [Sprint 09: Markdown] starts on 2025-05-10 and ends on 2025-05-24
|  |  | Design Adaptation | 2025-12-21 | 2026-01-04 | Sprint 24: Design Adaptation | [Sprint 24: Design Adaptation] starts on 2025-12-21 and ends on 2026-01-04 | [Sprint 24: Design Adaptation] is 0% complete | sprint | [Sprint 10: PlantUML & Latex] starts on 2025-05-25 and ends on 2025-06-08
|  |  | Regulatory Review | 2026-01-05 | 2026-01-19 | Sprint 25: Regulatory Review | [Sprint 25: Regulatory Review] starts on 2026-01-05 and ends on 2026-01-19 | [Sprint 25: Regulatory Review] is 0% complete | sprint | [Sprint 11: Content Safety API] starts on 2025-06-09 and ends on 2025-06-23
|  |  | User Acq. & Marketing plan | 2026-01-20 | 2026-02-03 | Sprint 26: User Acq. & Marketing plan | [Sprint 26: User Acq. & Marketing plan] starts on 2026-01-20 and ends on 2026-02-03 | [Sprint 26: User Acq. & Marketing plan] is 0% complete | sprint | [Sprint 12: Structure Sharing] starts on 2025-06-24 and ends on 2025-07-08
|  |  | Business Plan | 2026-02-04 | 2026-02-18 | Sprint 27: Business Plan | [Sprint 27: Business Plan] starts on 2026-02-04 and ends on 2026-02-18 | [Sprint 27: Business Plan] is 0% complete | sprint | [Sprint 13: Cross-Structure Reporting] starts on 2025-07-09 and ends on 2025-07-23
|  |  | Launch | 2026-02-17 |  | Launch | [Launch] happens on 2026-02-17 |  | event | [Sprint 14: User Metrics] starts on 2025-07-24 and ends on 2025-08-07
[Restricted Preview] starts on 2025-08-08 and ends on 2025-12-05
[Sprint 15: Platform Metrics & Alerting] starts on 2025-08-08 and ends on 2025-08-22
[Sprint 16: Test Automation ] starts on 2025-08-23 and ends on 2025-09-06
[Sprint 17: Web Analytics] starts on 2025-09-07 and ends on 2025-09-21
[Sprint 18: LLM Ingest] starts on 2025-09-22 and ends on 2025-10-06
[Sprint 19: Penetration Testing] starts on 2025-10-07 and ends on 2025-10-21
[Sprint 20: Cost Optimization] starts on 2025-10-22 and ends on 2025-11-05
[Sprint 21: Automated Scaling] starts on 2025-11-06 and ends on 2025-11-20
[Sprint 22: Payment Processing] starts on 2025-11-21 and ends on 2025-12-05
[Invite Preview] starts on 2025-12-06 and ends on 2026-02-18
[Sprint 23: Design Review] starts on 2025-12-06 and ends on 2025-12-20
[Sprint 24: Design Adaptation] starts on 2025-12-21 and ends on 2026-01-04
[Sprint 25: Regulatory Review] starts on 2026-01-05 and ends on 2026-01-19
[Sprint 26: User Acq. & Marketing plan] starts on 2026-01-20 and ends on 2026-02-03
[Sprint 27: Business Plan] starts on 2026-02-04 and ends on 2026-02-18
[Launch] happens on 2026-02-17
[Ideate] is 100% complete
[Proof of Concept] is 100% complete
[Sprint 00: Architect] is 100% complete
[Sprint 01: Design] is 100% complete
[Sprint 02: Backend] is 100% complete
[Sprint 03: Frontend] is 100% complete
[Sprint 04: Integrate] is 100% complete
[Sprint 05: Onboarding] is 100% complete
[Prototype] is 18% complete
[Sprint 06: Admin & Invites] is 100% complete
[Sprint 07: Renderer R&D] is 29% complete
[Sprint 08: Quill Enhancements - pictures, tables] is 0% complete
[Sprint 09: Markdown] is 0% complete
[Sprint 10: PlantUML & Latex] is 0% complete
[Sprint 11: Content Safety API] is 0% complete
[Sprint 12: Structure Sharing] is 0% complete
[Sprint 13: Cross-Structure Reporting] is 0% complete
[Sprint 14: User Metrics] is 0% complete
[Restricted Preview] is 0% complete
[Sprint 15: Platform Metrics & Alerting] is 0% complete
[Sprint 16: Test Automation ] is 0% complete
[Sprint 17: Web Analytics] is 0% complete
[Sprint 18: LLM Ingest] is 0% complete
[Sprint 19: Penetration Testing] is 0% complete
[Sprint 20: Cost Optimization] is 0% complete
[Sprint 21: Automated Scaling] is 0% complete
[Sprint 22: Payment Processing] is 0% complete
[Invite Preview] is 0% complete
[Sprint 23: Design Review] is 0% complete
[Sprint 24: Design Adaptation] is 0% complete
[Sprint 25: Regulatory Review] is 0% complete
[Sprint 26: User Acq. & Marketing plan] is 0% complete
[Sprint 27: Business Plan] is 0% complete
@endgantt